# EurekAlert! Effectiveness Research Project

Date: May 21, 2025

## Project Overview

This contracted research project aims to provide valuable insight into the effectiveness of EurekAlert!, a news release distribution platform, in facilitating scholarly impact for academic article authors, their home organizations, and publishers by comparing across several metrics. The project will focus on organizations and publishers in Japan and China.

## Project Objective

To determine whether there is empirical evidence that the use of EurekAlert! affects the scholarly and societal impact (henceforth simply “scholarly impact”) of individual articles and scholarly journal publishers through a range of metrics.

## Scope of Work

The project will study the effectiveness of news releases issued by the following organizations:

- Science Partner Journals

  - Advanced Devices & Instrumentation

  - Beijing Institute of Technology Press Co., Ltd, including:

    - Energy Material Advances

    - Space: Science & Technology

    - Cyborg and Bionic Systems

  - BioDesign Research 
As of January 2025, BioDesign Research is no longer published with AAAS. (Therefore this project will only assess the journal’s publications through end of 2024).

  - Biomaterials Research

  - BMEF (BME Frontiers)

  - Ecosystem Health and Sustainability

  - Health Data Science

  - Intelligent Computing

  - Journal of Bio-X Research

  - Journal of Remote Sensing

  - Ocean-Land-Atmosphere Research (OLAR)

  - Plant Phenomics
As of January 2025, BioDesign Research is no longer published with AAAS (Therefore this project will only assess the journal’s publications through end of 2024).

  - Research

  - Ultrafast Science

  - Journal of EMDR Practice and Research
SPJ has not purchased a subscription for this journal. Therefore this title could be used as a control.

- Chinese Academy of Science

  - Chinese Academy of Sciences Headquarters 
(The CAS Headquarters has posted releases on behalf of a number of institutes, as indicated in the associated news releases).

  - University of Science and Technology of China

  - Institute of Physics of the Czech Academy of Sciences

  - Institute of Process Engineering, Chinese Academy of Sciences

  - IGSNRR CAS

  - Institute of Atmospheric Physics, Chinese Academy of Sciences

  - Aerospace Information Research Institute, Chinese Academy of Sciences

  - Dalian Institute of Chemical Physics, Chinese Academy Sciences

  - Light Publishing Center, Changchun Institute of Optics, Fine Mechanics And Physics, CAS

  - Hefei Institutes of Physical Science, Chinese Academy of Sciences

  - Shenzhen Institute of Advanced Technology, Chinese Academy of Sciences

- Higher Education Press

- Tsinghua University Press

- Shanghai Jiao Tong University Journal Center

- Nagoya University

- Hokkaido University

- University of Tokyo

- University of Kyoto

- Osaka Metropolitan University
Formerly Osaka City University and Osaka Prefecture University

## Deliverables

Analysis of the effectiveness of news releases on EurekAlert! in driving scholarly impact using the following metrics:

- Citations (total; domestic vs. international)

- Altmetric Scores (for papers)

  - Number of patents that have mentioned this publication.

  - Number of policies that have mentioned this publication.

  - Number of news sources that have mentioned the publication.

  - Number of walls that have mentioned the output on Facebook.

  - Number of twitter accounts that have tweeted this publication.

  - Number of Bluesky accounts that have posted this publication.

  - Number of YouTube channels that have mentioned the output.

- Change in Impact Factor (for applicable journals)

- Patent Applications

- Policy Citations

- News Coverage

- Comparison of scholarly impact of papers with a news release on EurekAlert! against those similar quality and discipline without a news release on EurekAlert!

- Comparison of scholarly impact of papers that have not received any mainstream news coverage, between those with a news release on EurekAlert! and those without (ie. Removing mainstream news coverage as a factor in affecting scholarly impact).

## Timeline and Rates

Estimated Calendar Time to Complete Tasks:

- Gathering publication data for institutes and journals: ~2 days

- Matching publications to press release text: ~4–6 days

- Generating patent applications, news mentions, and policy citations: ~1 day

- Processing data and capture social media mentions: ~7 days

- Analyzing domestic vs. international citations and changes in impact factor: ~2 days

- Running comparisons (press release vs. no release, media coverage vs. none): ~2 days

Note: The matching process may be quicker if the posts include DOIs.

Estimated Active Working Time Required:

- Gathering publication data: ~4–5 hours

- Matching publications to press releases: ~3 hours

- Generating outcome variables: ~3 hours

- Social media analysis: ~10 hours

- Citation and impact factor analysis: ~5 hours

- Comparative analysis: ~5 hours

## Tasks and Responsibilities

EurekAlert! will provide data as soon as a contract has been signed and Scope of Work has been accepted.

EurekAlert! data requirements

EurekAlert! will provide the following data from its platform:

- A collection of all News Releases, in the form of Excel Spreadsheets, containing all publicly-available data, for the time frame of [Specify].

- For each organization selected for this study, EurekAlert! will also provide the following data:

  - Subscription dates

  - Submission volume (per subscription period)

Altmetric data requirements

EurekAlert! will facilitate access to the following Altmetric data:

| News | cited_by_msm_count | Number of news sources that have mentioned the publication. |
| --- | --- | --- |
| Policy | cited_by_policies_count | Number of policies that have mentioned this publication. |
| Patent | cited_by_patents_count | Number of patents that have mentioned this publication. |
| Social | cited_by_tweeters_count | Number of twitter accounts that have tweeted this publication. |
| Social | cited_by_bluesky_count | Number of Bluesky accounts that have posted this publication. |
| Social | cited_by_fbwalls_count | Number of walls that have mentioned the output on Facebook. |
| Social | cited_by_videos_count | Number of Youtube channels that have mentioned the output. |